## Gant Chart
HOLOSONIC GANTT CHART
OVERALL PROJECT STATUS |  | CURRENT MONTH |  | 2 |  | LAST EDITED | 2023-11-29
PROJECT TITLE |  | COMPANY NAME |  | Holosonic
PROJECT MANAGER |  | PROJECT START DATE |  | 2023-11-01
# | TASK TITLE | START DATE | END DATE | START MONTH | END MONTH | DURATION | PROGRESS | 2024 |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2023-11-01 to 2027-10-01
 | time axis 2023-11-01 to 2027-10-01
1 | Simulations | 2023-11-01 | 2024-08-30 | 1 | 36 | 9.9667 | 0%
| Initial Lit Review | 2023-11-01 | 2023-11-30 | 1 | 1 | 0.96667 | 100%
| 2D IASA and hologram reconstruction | 2023-11-01 | 2023-11-30 | 1 | 1 | 0.96667 | 0%
| 3D IASA and hologram reconstruction | 2023-12-01 | 2024-01-30 | 2 | 3 | 1.9667 | 0%
| COMSOL | 2023-12-01 | 2024-01-30 | 2 | 3 | 1.9667 | 0%
| Metamaterial design | 2024-07-01 | 2024-08-30 | 9 | 10 | 1.9667 | 0%
2 | Prototyping | 2023-12-01 | 2025-05-30 | 2 | 19 | 17.9667 | 0%
| 2D Prototype | 2023-12-01 | 2024-03-01 | 2 | 4 | 3 | 0%
| 3D Prototype | 2024-03-01 | 2024-06-30 | 5 | 8 | 3.9667 | 0%
| Metamaterial prototyping | 2024-09-01 | 2025-03-02 | 11 | 16 | 6.0333 | 0%
| Final Prototype | 2025-01-01 | 2025-05-30 | 15 | 19 | 4.9667 | 0%
3 | Testing | 2024-07-01 | 2025-05-30 | 9 | 19 | 10.9667 | 0%
| 3D Prototype user testing | 2024-07-01 | 2024-12-30 | 9 | 14 | 5.9667 | 0%
| Metamaterial lab testing | 2024-12-01 | 2025-03-02 | 14 | 16 | 3.0333 | 0%
| Final prototype user testing | 2025-03-01 | 2025-05-30 | 17 | 19 | 2.9667 | 0%
4 | Commercialization | #N/A | #N/A |  |  | #N/A | 0%
| Find suppliers | 2025-06-01 | 2025-08-30 | 20 | 22 | 2.9667 | 0%
| Quality assurance + customer feedback | 2025-09-01 | 2025-11-30 | 23 | 25 | 2.9667 | 0%
| Mass production | 2025-12-01 | 2026-03-02 | 26 | 28 | 3.0333 | 0%
| Sales distribution | 2026-01-01 | 2026-01-30 | 27 | 27 | 0.96667
| Customer feedback | 2026-02-01 | 2026-03-02 | 28 | 28 | 1.0333 | 0%
| Find new markets! | 2026-02-01 | 2026-03-02 | 28 | 28 | 1.0333 | 0%
5 | Business | 2024-04-01 | 2025-03-02 | 6 | 16 | 11.0333 | 0%
| Market targetted | 2024-04-01 | 2024-04-30 | 6 | 6 | 0.96667 | 0%
| Customer discovery | 2024-04-01 | 2024-07-30 | 6 | 9 | 3.9667 | 0%
| First VC funding | 2024-06-01 | 2024-06-30 | 8 | 8 | 0.96667 | 0%
| Hire materials scientist | 2024-06-01 | 2024-06-30 | 8 | 8 | 0.96667
| Acquire lab space | 2024-08-01 | 2024-08-30 | 10 | 10 | 0.96667 | 0%
| Patent finalized | 2024-12-01 | 2024-12-30 | 14 | 14 | 0.96667 | 0%
| Hire engineers, ops, manufacturing | 2025-02-01 | 2025-03-02 | 16 | 16 | 1.0333 | 0%
Formulas:
COMPANY NAME = MIN([COMPANY NAME, row below]:C14)

## Works
Start Date | 2023-11-01
1 | 2023-11-01
2 | 2023-12-01
3 | 2024-01-01
4 | 2024-02-01
5 | 2024-03-01
6 | 2024-04-01
7 | 2024-05-01
8 | 2024-06-01
9 | 2024-07-01
10 | 2024-08-01
11 | 2024-09-01
12 | 2024-10-01
13 | 2024-11-01
14 | 2024-12-01
15 | 2025-01-01
16 | 2025-02-01
17 | 2025-03-01
18 | 2025-04-01
19 | 2025-05-01
20 | 2025-06-01
21 | 2025-07-01
22 | 2025-08-01
23 | 2025-09-01
24 | 2025-10-01
25 | 2025-11-01
26 | 2025-12-01
27 | 2026-01-01
28 | 2026-02-01
29 | 2026-03-01
30 | 2026-04-01
31 | 2026-05-01
32 | 2026-06-01
33 | 2026-07-01
34 | 2026-08-01
35 | 2026-09-01
36 | 2026-10-01
37 | 2026-11-01
38 | 2026-12-01
39 | 2027-01-01
40 | 2027-02-01
41 | 2027-03-01
42 | 2027-04-01
43 | 2027-05-01
44 | 2027-06-01
45 | 2027-07-01
46 | 2027-08-01
47 | 2027-09-01
48 | 2027-10-01
T/ST/M/D | Task #'s | Task | Leader | Start date | End date | Start month | End month | Duration | Percentage | #REF! | #REF!
#REF! | 1 | Simulations | #REF! | 2023-11-01 | 2024-08-30 | 1 | 36 | 9.9667 | 0 | #REF!
#REF! | 0 | Initial Lit Review | #REF! | 2023-11-01 | 2023-11-30 | 1 | 1 | 0.96667 | 100%
#REF! | 0 | 2D IASA and hologram reconstruction | #REF! | 2023-11-01 | 2023-11-30 | 1 | 1 | 0.96667 | 0%
#REF! | 0 | COMSOL | #REF! | 2023-12-01 | 2024-01-30 | 2 | 3 | 1.9667 | 0%
#REF! | 0 | Metamaterial design | #REF! | 2024-07-01 | 2024-08-30 | 9 | 10 | 1.9667 | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | 2 | Prototyping | #REF! | 2023-12-01 | 2025-05-30 | 2 | 19 | 17.9667 | 0% | #REF!
#REF! | 0 | 2D Prototype | #REF! | 2023-12-01 | 2024-03-01 | 2 | 4 | 3 | 0%
#REF! | 0 | 3D Prototype | #REF! | 2024-03-01 | 2024-06-30 | 5 | 8 | 3.9667 | 0%
#REF! | 0 | Metamaterial prototyping | #REF! | 2024-09-01 | 2025-03-02 | 11 | 16 | 6.0333 | 0%
#REF! | 0 | Final Prototype | #REF! | 2025-01-01 | 2025-05-30 | 15 | 19 | 4.9667 | 0%
#REF! | 0 | 3D Prototype user testing | #REF! | 2024-07-01 | 2024-12-30 | 9 | 14 | 5.9667 | 0%
#REF! | 0 | Metamaterial lab testing | #REF! | 2024-12-01 | 2025-03-02 | 14 | 16 | 3.0333 | 0%
#REF! | 0 | Final prototype user testing | #REF! | 2025-03-01 | 2025-05-30 | 17 | 19 | 2.9667 | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | 5 | Business | #REF! | 2024-04-01 | 2025-03-02 | 6 | 16 | 11.0333 | 0% | #REF!
#REF! | 0 | Market targetted | #REF! | 2024-04-01 | 2024-04-30 | 6 | 6 | 0.96667 | 0%
#REF! | 0 | First VC funding | #REF! | 2024-06-01 | 2024-06-30 | 8 | 8 | 0.96667 | 0%
#REF! | 0 | Acquire lab space | #REF! | 2024-08-01 | 2024-08-30 | 10 | 10 | 0.96667 | 0%
#REF! | 0 | Patent finalized | #REF! | 2024-12-01 | 2024-12-30 | 14 | 14 | 0.96667 | 0%
#REF! | 0 | Hire engineers, ops, manufacturing | #REF! | 2025-02-01 | 2025-03-02 | 16 | 16 | 1.0333 | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 26 | 48 | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!
#REF! | 0 | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | #REF!

## Gantt Chart (hidden)
| GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
| PROJECT TITLE |  | EE0009957 |  |  |  |  | COMPANY NAME | [6 empty] | Littoral Power Systems
| PROJECT MANAGER |  | Sydney Platt |  |  |  |  | PROJECT START DATE | [6 empty] | 2022-11-15
| Task Numbers | TASK TITLE | TASK OWNER | START DATE | DUE DATE |  |  | DURATION | PCT OF TASK COMPLETE | BP1 | [21 empty] | BP2
[6 empty] | START MONTH | END MONTH |  |  | 2022 |  |  | 2023 | [17 empty] | 20 | 24 |  |  |  |  | 2025 | [11 empty] | 2026
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
[10 empty] | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O
Budget Period 2 Begins
T | 0 | Project Management | LPS |  |  | 1 | 48
ST | 0.1 | Project Management Plan |  | 2022-11-15 |  | 1 | 1 | 1 | 0%
M | M0.1.1 | Project management plan is complete. |  |  |  | 1 | 1 | 1 | 0%
D | D0.1.1 | Project management plan (5–10-page document that augments the SOPO and RPPR2) |  |  |  | 2 | 2 | 1 | 0%
ST | 0.2 | Diversity, Equity and Inclusion Plan |  |  |  | 1 | 48 | 48 | 0%
M | M0.2.1 | Identified economically challenged coastal communities (such as Angoon AK) and reported on the alignment of this technology with the community’s needs as part of the Go/No-Go |  |  |  | 22 | 22 | 1 | 0% | bar: 20 22 A
M | M0.2.2 | Established a written employee recruitment plan |  |  |  | 6 | 6 | 1 | 0%
D | D0.2.1 | Employee recruitment plan |  |  |  | 7 | 7 | 1 | 0%
M | M0.2.3 | Implemented a key element of the recruiting plan, e.g., attended a career fair |  |  |  | 16 | 16 | 1 | 0%
M | M0.2.4 | Implemented another key element of the recruiting plan, e.g., attended another career fair |  |  |  | 36 | 36 | 1 | 0%
M | M0.2.5 | Subaward template modified to include the requirement that subrecipients provide a DEI plan and that they report on progress against that plan for the Go/No-Go and at the end of the project |  |  |  | 2 | 2 | 1 | 0%
M | M0.2.6 | Established a plan to provide outreach and education about this project |  |  |  | 15 | 15 | 1 | 0%
D | D0.2.2 | DEI engagement plan |  |  |  | 15 | 15 | 1 | 0%
M | M0.2.7 | Implemented a key element of the outreach plan, e.g., partnered with TRiO and gave a talk at New Bedford High School |  |  |  | 24 | 24 | 1 | 0%
D | D0.2.3 | Reoccurring Diversity, Equity, and Inclusion Activities Project Reporting as part of quartlery Research Performance Progress Report (RPPR) |  |  |  | 1 | 48 | 48 | 0%
ST | 0.3 | Develop preliminary commercialization plan |  |  |  | 1 | 48 | 48 | 0%
M | M0.3.1 | Conversations with 5 potential customers are complete and notes from each have been recorded |  |  |  | 8 | 8 | 1 | 0%
D | D0.3.1 | House of Quality analysis report |  |  |  | 16 | 16 | 1 | 0%
M | M0.3.2 | Customer conversations have been analyzed to determine the most feasible market to pursue |  |  |  | 20 | 20 | 1 | 0% | bar: 2023 20 J
M | M0.3.3 | Minimum viable product (MVP) and pricing strategy have been specified. |  |  |  | 27 | 27 | 1 | 0%
M | M0.3.4 | Key risks to producing the MVP have been identified |  |  |  | 40 | 40 | 1 | 0%
D | D0.3.2 | Preliminary Commercialization Plan |  |  |  | 48 | 48 | 1 | 0%
ST | 0.4 | Manage Risks |  |  |  | 1 | 48 | 48 | 0%
D | D0.4.1 | Updated project and technical risk register delivered at start of project and updated for Go/No Go aplication |  |  |  | 19 | 19 | 1 | 0%
ST | 0.5 | Data Management Plan |  |  |  | 1 | 48 | 48 | 0%
T | 1 | Develop wave estimation technique and the NeuralWEC supervisory control | GE |  |  | 1 | 19
ST | 1.1 | Develop preliminary version of AI-based Fast Surrogate Model (AIFSM) of the plant |  | 2022-11-02 | 2023-05-02 | 2 | 7 | 6 | 0% | bar: 2022 2 D to 2023 7 M
M | M 1.1.1. | WEC-Sim model, baseline controller, sensor model and API supplied to controls software experts. |  | - |  | 2 | 2 | - | 0% | bar: 2022 2 D
ST | 1.2 | Receive, test, and benchmark preliminary WEC-Sim model |  | 2022-11-03 | 2022-12-03 | 2 | 2 | 1 | 0% | bar: 2022 2 D
ST | 1.3 | Develop preliminary version of the scheduled full-state MPC-based controllers |  | 2022-11-04 | 2023-04-04 | 2 | 6 | 5 | 0% | bar: 2022 2 D to 2023 6 A
M | M1.3.1 | The controller is demonstrated on WEC-Sim model |  | - |  | 6 | 6 | - | 0%
ST | 1.4 | Develop preliminary version of RLE for estimation of wave forcing based on sea states |  | 2022-11-05 | 2023-07-05 | 2 | 9 | 8 | 0% | bar: 2022 2 D to 2023 9 J
ST | 1.5 | Collaborate on wave tank test plan and wave tank sensor selection |  | 2022-11-06 | 2023-02-06 | 2 | 4 | 3 | 0% | bar: 2022 2 D to 2023 4 F
ST | 1.6 | Update MPC control strategy for use with developed RLE |  | 2023-03-01 | 2023-10-01 | 6 | 12 | 7 | 0% | bar: 2023 6 A to 2023 12 O
ST | 1.7 | Deploy first versions of RLE/MPC on selected control platform |  | 2023-04-01 | 2023-10-01 | 7 | 12 | 6 | 0% | bar: 2023 7 M to 2023 12 O
M | M1.7.1 | RLE and controller deployed on control platform |  | - |  | 12 | 12 | - | 0% | bar: 2023 8 J to 2023 11 S
ST | 1.7.1 | Process ocean buoy wave data using RLE in emulator mode |  | 2023-05-01 | 2023-09-01 | 8 | 11 | 4 | 0% | bar: 2023 8 J to 2023 11 S
ST | 1.8 | Control hardware integration |  | 2023-06-01 | 2023-09-01 | 10 | 12 | 3 | 0% | bar: 2023 10 A to 2023 12 O
ST | 1.9 | Refine controller and RLE |  | 2023-08-01 | 2024-05-01 | 11 | 19 | 9 | 0% | bar: 2023 11 S to 2023 19 M
ST | 1.1 | Finalize selection of desired measurements and collaborate on sensor selection for the P2 |  | 2024-01-01 | 2024-03-01 | 16 | 17 | 2 | 0% | bar: 2023 16 F to 2023 17 M
ST | 1.11 | Continuing Application’s controller and RLE components |  | 2024-03-01 | 2024-05-01 | 18 | 19 | 2 | 0% | bar: 2023 18 A to 2023 19 M
ST | 1.12 | Documentation and packaging of RLE and MPC |  | 2024-05-01 | 2024-08-01 | 20 | 22 | 3 | 0% | bar: 2023 20 J to 20 22 A
D | D1.12.1 | RLE & MPC development code on Github and deployed on selected control hardware for wave tank testing. |  | - |  | 22 | 22 | - | 0% | bar: 2023 20 J to 20 22 A
D | D1.12.2 | Data, including any tabular data, time series data, code, software, or APIs suitable for public release should be uploaded to the MHK data repository or MHKDR. |  |  |  | 22 | 22 |  | 0% | bar: 2023 20 J to 20 22 A
T | 1B | Wave Measurement (Wave-by-Wave Spotter Buoy Development and Field Testing) |  |  |  | 1 | 17
ST | 1B.1 | Near Real-Time RF Spotter Buoy Customization |  | 2022-10-01 | 2023-04-01 | 1 | 6 | 6 | 0% | bar: 2022 1 N to 2023 6 A
|  | Develop preliminary spotter sync code |  | 2022-10-02 | 2023-04-02 |  |  | 6 | 0% | bar: 2022 1 N to 2023 6 A
ST | 1B.2 | Open ocean Deployment Campaign #1 with Spotter Buoys (PacWave Test Facility South) |  | 2022-10-01 | 2022-11-01 | 7 | 7 | 1 | 0% | bar: 2023 7 M
M | M1B.2.1 | Spotter Buoy Measurement Campaign #1 Complete |  | - |  | 7 | 7 | - | 0% | bar: 2023 7 M
M | M1B.2.2 | Preliminary spotter buoy assessment complete |  | 2023-05-01 | 2023-06-01 | 7 | 7 | 1 | 0% | bar: 2023 7 M
ST | 1B.2.1 | Permitting |  | 2022-10-02 | 2023-04-02 | 1 | 6 | 6 | 0% | bar: 2022 1 N to 2023 6 A
|  | File NEPA documentation for campaign #1 and 2 |  | 2022-10-01 | 2022-11-01 |  |  | 1 | 0% | bar: 2022 1 N
|  | Obtain NEPA authorization for campaign #1 and 2 |  | 2023-03-01 | 2023-04-01 |  |  | 1 | 0% | bar: 2023 6 A
|  | Deploy spotter array and carry out system test |  | 2023-05-01 | 2023-06-01 |  |  | 1 | 0% | bar: 2023 7 M
|  | Improve on spotter sync codes |  | 2023-05-02 | 2023-06-02 |  |  | 1 | 0% | bar: 2023 7 M to 2023 14 D
ST | 1B.3 | Interface development near real-time wave measurement code and RLE |  | 2023-05-02 | 2023-08-02 | 8 | 10 | 3 | 0% | bar: 2023 8 J to 2023 10 A
ST | 1B.4 | Open ocean Deployment Campaign #2 with near Real-Time Spotter Buoys and estimator |  | 2023-06-01 | 2023-07-01 | 15 | 15 | 1 | 0% | bar: 2023 15 J
|  | Further development of spotter sync code |  | 2023-10-01 | 2024-02-01 |  |  | 4 | 0% | bar: 2023 14 D to 2023 17 M
|  | Deploy spotter array and carry out system at test site, to gather data for training estimator, and to prove out real time data transmission |  | 2023-04-06 | 2023-09-06 |  |  | 5 | 0% | bar: 2023 15 J
M | M1B.4.1 | Near Real-Time Spotter Buoy (with estimator) Campaign #2 Complete |  | - |  | 15 | 15 | - | 0% | bar: 2023 15 J
D | D1B.4.1 | Measurement campaign #1 and 2 report with results and lessons learned |  |  |  | 16 | 16 |  | 0% | bar: 2023 15 J
T | 2 | Plan, prepare, perform wave tank testing; analyze results |  |  |  | 1 | 16
ST | 2.1 | Develop wave tank test plans |  | 2022-10-01 | 2023-02-01 | 1 | 4 | 4 | 0% | bar: 2022 1 N to 2023 4 F
ST | 2.2 | Provide and prepare P1 |  | 2023-03-01 | 2023-07-01 | 6 | 9 | 4 | 0% | bar: 2023 6 A to 2023 9 J
ST | 2.2.1 | Fabricate and order refurbishment parts for P1 |  | 2022-10-01 | 2023-03-01 | 1 | 5 | 5 | 0% | bar: 2022 1 N to 2023 5 M
ST | 2.2.2 | Develop and build v1 of power electronics package |  | 2022-10-01 | 2023-02-01 | 1 | 4 | 4 | 0% | bar: 2022 1 N to 2023 4 F
ST | 2.3 | Carry out tank test cycle #1 and analyze results |  | 2023-09-01 | 2023-10-01 | 12 | 12 | 1 | 0% | bar: 2023 12 O
M | M2.3.1 | Hydrodynamic parameters obtained for use in refining WEC-Sim model and baseline controller performance established |  | - |  | 12 | 12 | - | 0% | bar: 2023 12 O
ST | 2.4 | Carry out tank test cycle #2 and analyze results |  | 2023-11-01 | 2023-12-01 | 14 | 14 | 1 | 0% | bar: 2023 14 D
M | M2.4.1 | Initial NeuralWEC system wave tank testing complete. Analyze results and compare to goal metrics in Table 1 and anticipated simulation findings |  | - |  | 14 | 14 | - | 0% | bar: 2023 14 D
ST | 2.5 | Carry out tank test cycle #3 and analyze results |  | 2024-01-01 | 2024-02-01 | 16 | 16 | 1 | 0% | bar: 2023 16 F
M | M2.5.1 | Wave tank testing is complete. Analyze results and compare to goal metrics in Table 1 as well as previous wave tank test. |  | - |  | 16 | 16 | - | 0% | bar: 2023 16 F
D | D2.5.1 | Wave tank testing report for all three tests with results vs goal metrics and lessons learned |  |  |  | 17 | 17 |  | 0% | bar: 2023 16 F
M | M2.5.2 | DOE review |  |  |  | 16 | 16 |  | 0% | bar: 2023 16 F
T | 3 | Develop a critical design for P2 |  |  |  | 1 | 19
ST | 3.1 | Define requirements |  | 2022-10-01 | 2022-12-01 | 1 | 2 | 2 | 0% | bar: 2022 1 N to 2022 2 D
ST | 3.2 | Develop design for P2 in WEC-Sim |  | 2023-01-01 | 2023-04-01 | 3 | 5 | 3 | 0% | bar: 2022 3 J to 2023 5 M
ST | 3.3 | Develop CAD model and shop drawings |  | 2023-05-01 | 2024-05-01 | 6 | 19 | 12 | 0% | bar: 2023 6 A to 2023 18 A
D | D3.3.1 | 90% critical design for the P2 included in the continuation application and Go/No-Go presentation. |  | - |  | 19 | 19 | - | 0% | bar: 2023 18 A
T | 4 | Develop preliminary plans for fabricating, IO&M, testing & decommissioning P2 at PacWave |  |  |  | 1 | 22
ST | 4.1 | Preliminary contractual agreements with PacWave facility |  | 2023-07-01 | 2024-07-01 | 10 | 22 | 12 | 0% | bar: 2023 10 A to 20 22 A
ST | 4.2 | Develop preliminary test plan for PacWave |  | 2022-10-01 | 2024-08-01 | 2 | 19 | 22 | 0% | bar: 2022 1 N to 2023 19 M
D | D4.2.1 | P2 Testing Plan |  |  |  | 19 | 19 |  | 0% | bar: 2023 6 A to 2023 19 M
ST | 4.3 | Develop fabrication plan for PacWave |  | 2023-03-01 | 2024-08-01 | 6 | 19 | 17 | 0% | bar: 2023 6 A to 2023 19 M
M | M4.3.1 | 30% plan set for fabrication, mobilization, deployment and decommissioning. |  | - |  |  |  | - | 0% | bar: 2023 19 M
M | M4.3.2 | 60% plan set for fabrication, mobilization, deployment and decommissioning. |  | - |  |  |  | - | 0% | bar: 2023 19 M
D | D4.3.1 | Preliminary fabrication plan |  |  |  | 19 | 19 |  | 0% | bar: 2023 17 M to 2023 19 M
ST | 4.4 | Develop preliminary plans for mobilization, deployment and decommissioning, including safety training and emergency response plans |  | 2023-03-01 | 2024-08-01 | 6 | 19 | 17 | 0% | bar: 2023 6 A to 2023 19 M
ST | 4.4.1 | Submit NEPA documentation/Biological Assessment for testing the P2 at PacWave South |  | 2024-04-01 | 2024-05-01 | 19 | 22 | 1 | 0% | bar: 2023 19 M to 20 22 A
D | D4.4.1 | Preliminary IO&M plan including decommissioning of P2 |  |  |  | 19 | 19 |  | 0% | bar: 2023 19 M
T | 5 | Go/No-Go Review |  |  |  | 19 | 22
D | D5.0.1 | Continuation application including preliminary P2 design and budget (may include additional technical documentation identified in BP1) |  |  |  | 19 | 19 |  | 0% | bar: 2023 19 M to 20 22 A
D | D5.0.2 | GNG virtual presentation |  |  |  | 19 | 19 |  | 0% | bar: 2023 19 M to 20 22 A
M | M5.0.1 | Go/No-Go Decision Received |  |  |  | 19 | 19 |  | 0% | bar: 2023 19 M to 20 22 A
ST | 5.1 | Negotiations of BP2 (or Closeout of BP1) depending on the GNG decision |  | 45383 | 2024-05-01 | 20 | 22 | 1 | 0% | bar: 2023 19 M to 20 22 A
ST | 5.2.1 | Bridge tasks occur |  | 2024-05-01 | 2024-08-01 | 20 | 22 | 3 | 0% | bar: 2023 20 J to 20 22 A
BP | Budget Period 2 Begins
T | 6 | Update design and plan set for P2 based on DOE feedback |  |  |  | 23 | 48
ST | 6.1 | Detailed engineering drawings, fabrication plans, test plans, deployment/ decommissioning plans |  | 2024-08-01 | 2024-12-01 | 23 | 26 | 4 | 0% | bar: 24 23 S to 24 26 D
D | D6.1.1 | Detailed engineering drawings |  | 2024-11-30 | 2024-11-30 | 26 | 26 | 0 | 0% | bar: 24 26 D
D | D6.1.2 | Detailed test plan |  | 2024-11-30 | 2024-11-30 | 26 | 26 | 0 | 0% | bar: 24 26 D
D | D6.1.3 | Detailed IO&M and decommissioning plan |  | 2024-11-30 | 2024-11-30 | 26 | 26 | 0 | 0% | bar: 24 26 D
D | D6.1.4 | Detailed Fabrication Plan |  | 2024-11-30 | 2024-11-30 | 26 | 26 | 0 | 0% | bar: 24 26 D
M | M6.1.1 | DOE design review completed |  | 2025-01-01 | 2025-01-01 | 26 | 26 | 0 | 0% | bar: 24 26 D to 24 27 J
ST | 6.2 | Consultation regarding updating control for PacWave |  | 2024-08-01 | 2026-09-01 | 23 | 48 | 25 | 0% | bar: 24 23 S to 2026 48 O
ST | 6.3 | Software maturation and data analysis |  | 2024-09-01 | 2024-12-01 | 24 | 26 | 3 | 0% | bar: 24 24 O to 24 26 D
ST | 6.4 | Purchase long lead items (e.g. generators, composite parts requiring tooling, etc., typical motor/generator quoted at 32-wk lead time, position indexer quoted at 43 wk lead time) |  | 2023-08-01 | 2024-02-01 | 23 | 29 | 6 | 0% | bar: 24 23 S to 2025 29 M
T | 7 | Fabricate P2 |  |  |  | 24 | 41
ST | 7.1 | Composite fabrication |  | 2024-09-01 | 2025-06-01 | 24 | 36 | 9 | 0% | bar: 2025 28 F to 2025 36 O
ST | 7.2 | Metal fabrication |  | 2024-11-01 | 2025-06-01 | 26 | 36 | 7 | 0% | bar: 2025 29 M to 2025 36 O
ST | 7.3 | Generator and electrical component procurement |  | 2024-12-01 | 2025-06-01 | 27 | 38 | 6 | 0% | bar: 2025 33 J to 2025 38 D
ST | 7.4 | Assembly and fabrication inspection by DOE |  | 2024-06-01 | 2024-07-01 | 33 | 39 | 1 | 0% | bar: 2025 39 J
ST | 7.5 | Ship to Port of Newport, OR |  | 2024-06-01 | 2024-07-01 | 33 | 40 | 1 | 0% | bar: 2026 40 F
M | M7.5.1 | P2 delivered to test site |  | - |  | 33 | 40 | - | 0% | bar: 2026 40 F
M | M7.5.2 | DOE Review |  |  |  | 41 | 41 | bar: 2026 40 F
T | 8 | Deploy P2 per plan developed in Subtask 4.4 and finalized in Task 6 |  |  |  | 34 | 41
ST | 8.1 | Staging |  | 2024-07-01 | 2024-08-01 | 34 | 41 | 1 | 0% | bar: 2026 41 M
ST | 8.2 | Load-in and assembly |  | 2024-07-02 | 2024-08-02 | 34 | 41 | 1 | 0% | bar: 2026 41 M
ST | 8.3 | Final survey/reconnaissance of PacWave test berth |  | 2024-07-03 | 2024-08-03 | 34 | 41 | 1 | 0% | bar: 2026 41 M
ST | 8.4 | Set mooring, connect umbilical cable, and deploy WEC & Spotters |  | 2024-07-04 | 2024-08-04 | 34 | 41 | 1 | 0% | bar: 2026 41 M
T | 9 | Test P2 at PacWave South, per plan developed in Subtask 4.4 and finalized in Task 6 |  |  |  | 34 | 45
D | D9.01 | P2 / MPC / RLE Test and Operations Report |  |  |  | 45 | 45 |  | 0% | bar: 2026 42 A
D | D9.02 | Data delivered to MHKDR/Tethys/Tethys Engineering |  |  |  | 45 | 45 |  | 0% | bar: 2026 42 A
ST | 9.1 | Baseline testing |  | 45505 | 2024-09-01 | 35 | 42 | 1 | 0% | bar: 2026 42 A
ST | 9.2 | MPC and RLE testing with continual evaluation |  | 2024-09-01 | 2024-12-01 | 36 | 45 | 3 | 0% | bar: 2026 43 M to 2026 45 J
ST | 9.3 | P2 performance analysis/ Accreditation testing |  | 2024-10-01 | 2024-12-01 | 37 | 45 | 2 | 0% | bar: 2026 44 J to 2026 45 J
T | 10 | Decommission P2 per plan developed in Subtask 4.4 and finalized in Task 6 |  |  |  | 39 | 46
D | D10.0.1 | Decomissioning report and lessons learned |  |  |  | 46 | 46 |  | 0% | bar: 2026 46 A
ST | 10.1 | Safety reconnaissance |  | 2024-12-01 | 2025-01-01 | 39 | 46 | 1 | 0% | bar: 2026 46 A
ST | 10.2 | P2 and Spotter buoy retrieval |  | 2024-12-02 | 2025-01-02 | 39 | 46 | 1 | 0% | bar: 2026 46 A
ST | 10.3 | Cable & mooring retrieval |  | 2024-12-03 | 2025-01-03 | 39 | 46 | 1 | 0% | bar: 2026 46 A
ST | 10.4 | Anchor retrieval |  | 2024-12-04 | 2025-01-04 | 39 | 46 | 1 | 0% | bar: 2026 46 A
ST | 10.5 | Clean, disassemble, inventory and store equipment for future use |  | 2024-12-05 | 2025-01-05 | 39 | 46 | 1 | 0% | bar: 2026 46 A
T | 11 | Final analysis and report |  |  |  | 43 | 48
ST | 11.1 | Update WEC-Sim full sized device simulation |  | 2024-04-01 | 2024-09-01 | 43 | 47 | 5 | 0% | bar: 2026 43 M to 2026 47 S
D | D11.1.1 | Data submitted to MHKDR/Tethys/Tethys Engineering |  |  |  | 48 | 48 |  | 0% | bar: 2026 46 A to 2026 48 O
ST | 11.2 | Compare WEC-Sim results to Table 1 |  | 2024-07-01 | 2024-10-01 | 46 | 48 | 3 | 0% | bar: 2026 46 A to 2026 48 O
ST | 11.3 | Write the Final Technical Report |  | 2024-09-01 | 2024-10-01 | 48 | 48 | 1 | 0% | bar: 2026 48 O
D | D11.3.1 | Final Technical Report including final project goal metrics results |  |  |  | 48 | 48
D | D11.3.2 | LCOE analysis using SAM |  |  |  | 48 | 48
Formulas:
DUE DATE = DATE(YEAR([START DATE]),MONTH([START DATE])+[COMPANY NAME],DAY([START DATE]))
Note on C133: argument for this subtask not being necessary since it is fully detailed in task 9 -Sydney Platt

## OG Gantt Chart (for Comparison) (hidden)
DE-EE-0009957 GANTT CHART
| OVERALL PROJECT STATUS |  | Green.red. yellow??? set this up base on current date, percentage of task supposed to be done by current datea nd percentage actually done by current date. |  |  |  |  | CURRENT DATE | [6 empty] | 2023-12-10 23:13 | [6 empty] | LAST EDITED | [6 empty] | 2022-10-06
| PROJECT TITLE |  | EE0009957 |  |  |  |  | COMPANY NAME | [6 empty] | Littoral Power Systems
| PROJECT MANAGER |  | Sydney Platt |  |  |  |  | PROJECT START DATE | [6 empty] | 2022-11-15
| TASK NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE |  |  | DURATION | PCT OF TASK COMPLETE | BP1 | [21 empty] | BP2
[6 empty] | START MONTH | END MONTH |  |  | 2022 |  |  | 2023 | [17 empty] | 20 | 24 |  |  |  |  | 2025 | [11 empty] | 2026
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2022-11-15 to 2026-10-15
 | time axis 2023-11-01 to 2027-10-01
 | time axis 2023-11-01 to 2027-10-01
Budget Period 2 Begins
T | 0 | Project Management | LPS | #NAME? | #NAME? | 1 | 48
ST | 0.1 | Project Management Plan |  | #NAME? | #NAME? | 1 | 1 | 1 | 0%
M | M0.1.1 | Project management plan is complete. |  | #NAME? | #NAME? | 1 | 1 | 1 | 0%
D | D0.1.1 | Project management plan (5–10-page document that augments the SOPO and RPPR2) |  | #NAME? | #NAME? | 2 | 2 | 1 | 0%
ST | 0.2 | Diversity, Equity and Inclusion Plan |  | #NAME? | #NAME? | 1 | 48 | 48 | 0%
M | M0.2.1 | Identified economically challenged coastal communities (such as Angoon AK) and reported on the alignment of this technology with the community’s needs as part of the Go/No-Go |  | #NAME? | #NAME? | 22 | 22 | 1 | 0%
M | M0.2.2 | Established a written employee recruitment plan |  | #NAME? | #NAME? | 6 | 6 | 1 | 0%
D | D0.2.1 | Employee recruitment plan |  | #NAME? | #NAME? | 7 | 7 | 1 | 0%
M | M0.2.3 | Implemented a key element of the recruiting plan, e.g., attended a career fair |  | #NAME? | #NAME? | 16 | 16 | 1 | 0%
M | M0.2.4 | Implemented another key element of the recruiting plan, e.g., attended another career fair |  | #NAME? | #NAME? | 36 | 36 | 1 | 0%
M | M0.2.5 | Subaward template modified to include the requirement that subrecipients provide a DEI plan and that they report on progress against that plan for the Go/No-Go and at the end of the project |  | #NAME? | #NAME? | 2 | 2 | 1 | 0%
M | M0.2.6 | Established a plan to provide outreach and education about this project |  | #NAME? | #NAME? | 15 | 15 | 1 | 0%
D | D0.2.2 | DEI engagement plan |  | #NAME? | #NAME? | 15 | 15 | 1 | 0%
M | M0.2.7 | Implemented a key element of the outreach plan, e.g., partnered with TRiO and gave a talk at New Bedford High School |  | #NAME? | #NAME? | 24 | 24 | 1 | 0%
D | D0.2.3 | Reoccurring Diversity, Equity, and Inclusion Activities Project Reporting as part of quartlery Research Performance Progress Report (RPPR) |  | #NAME? | #NAME? | 1 | 48 | 48 | 0%
ST | 0.3 | Develop preliminary commercialization plan |  | #NAME? | #NAME? | 1 | 48 | 48 | 0%
M | M0.3.1 | Conversations with 5 potential customers are complete and notes from each have been recorded |  | #NAME? | #NAME? | 8 | 8 | 1 | 0%
D | D0.3.1 | House of Quality analysis report |  | #NAME? | #NAME? | 16 | 16 | 1 | 0%
M | M0.3.2 | Customer conversations have been analyzed to determine the most feasible market to pursue |  | #NAME? | #NAME? | 20 | 20 | 1 | 0%
M | M0.3.3 | Minimum viable product (MVP) and pricing strategy have been specified. |  | #NAME? | #NAME? | 27 | 27 | 1 | 0%
M | M0.3.4 | Key risks to producing the MVP have been identified |  | #NAME? | #NAME? | 40 | 40 | 1 | 0%
D | D0.3.2 | Preliminary Commercialization Plan |  | #NAME? | #NAME? | 48 | 48 | 1 | 0%
ST | 0.4 | Manage Risks |  | #NAME? | #NAME? | 1 | 48 | 48 | 0%
D | D0.4.1 | Updated project and technical risk register delivered at start of project and updated for Go/No Go aplication |  | #NAME? | #NAME? | 19 | 19 | 1 | 0%
ST | 0.5 | Data Management Plan |  | #NAME? | #NAME? | 1 | 48 | 48 | 0%
T | 1 | Develop wave estimation technique and the NeuralWEC supervisory control | LPS | #NAME? | #NAME? | 1 | 19
ST | 1.1 | Develop preliminary version of AI-based Fast Surrogate Model (AIFSM) of the plant |  | #NAME? | #NAME? | 2 | 7 | 6 | 0% | bar: 2023-12-01 to 2024-05-01
M | M 1.1.1. | WEC-Sim model, baseline controller, sensor model and API supplied to controls software experts. |  | #NAME? | #NAME? | 2 | 2 | - | 0% | bar: 2023-12-01
ST | 1.2 | Receive, test, and benchmark preliminary WEC-Sim model |  | #NAME? | #NAME? | 2 | 2 | 1 | 0% | bar: 2023-12-01
ST | 1.3 | Develop preliminary version of the scheduled full-state MPC-based controllers |  | #NAME? | #NAME? | 2 | 6 | 5 | 0% | bar: 2023-12-01 to 2024-04-01
M | M1.3.1 | The controller is demonstrated on WEC-Sim model |  | #NAME? | #NAME? | 6 | 6 | - | 0%
ST | 1.4 | Develop preliminary version of RLE for estimation of wave forcing based on sea states |  | #NAME? | #NAME? | 2 | 9 | 8 | 0% | bar: 2023-12-01 to 2024-07-01
ST | 1.5 | Collaborate on wave tank test plan and wave tank sensor selection |  | #NAME? | #NAME? | 2 | 4 | 3 | 0% | bar: 2023-12-01 to 2024-02-01
ST | 1.6 | Update MPC control strategy for use with developed RLE |  | #NAME? | #NAME? | 6 | 12 | 7 | 0% | bar: 2024-04-01 to 2024-10-01
ST | 1.7 | Deploy first versions of RLE/MPC on selected control platform |  | #NAME? | #NAME? | 7 | 12 | 6 | 0% | bar: 2024-05-01 to 2024-10-01
M | M1.7.1 | RLE and controller deployed on control platform |  | #NAME? | #NAME? | 12 | 12 | - | 0% | bar: 2024-06-01 to 2024-09-01
ST | 1.7.1 | Process ocean buoy wave data using RLE in emulator mode |  | #NAME? | #NAME? | 8 | 11 | 4 | 0% | bar: 2024-06-01 to 2024-09-01
ST | 1.8 | Control hardware integration |  | #NAME? | #NAME? | 10 | 12 | 3 | 0% | bar: 2024-08-01 to 2024-10-01
ST | 1.9 | Refine controller and RLE |  | #NAME? | #NAME? | 11 | 19 | 9 | 0% | bar: 2024-09-01 to 2025-05-01
ST | 1.1 | Finalize selection of desired measurements and collaborate on sensor selection for the P2 |  | #NAME? | #NAME? | 16 | 17 | 2 | 0% | bar: 2025-02-01 to 2025-03-01
ST | 1.11 | Continuing Application’s controller and RLE components |  | #NAME? | #NAME? | 18 | 19 | 2 | 0% | bar: 2025-04-01 to 2025-05-01
ST | 1.12 | Documentation and packaging of RLE and MPC |  | #NAME? | #NAME? | 20 | 22 | 3 | 0% | bar: 2025-06-01 to 2025-08-01
D | D1.12.1 | RLE & MPC development code on Github and deployed on selected control hardware for wave tank testing. |  | #NAME? | #NAME? | 22 | 22 | - | 0% | bar: 2025-06-01 to 2025-08-01
D | D1.12.2 | Data, including any tabular data, time series data, code, software, or APIs suitable for public release should be uploaded to the MHK data repository or MHKDR. |  | #NAME? | #NAME? | 22 | 22 |  | 0% | bar: 2025-06-01 to 2025-08-01
T | 1B | Wave Measurement (Wave-by-Wave Spotter Buoy Development and Field Testing) | LPS | #NAME? | #NAME? | 1 | 17
ST | 1B.1 | Near Real-Time RF Spotter Buoy Customization |  | #NAME? | #NAME? | 1 | 6 | 6 | 0% | bar: 2023-11-01 to 2024-04-01
|  | Develop preliminary spotter sync code |  | #NAME? | #NAME? |  |  | 6 | 0% | bar: 2023-11-01 to 2024-04-01
ST | 1B.2 | Open ocean Deployment Campaign #1 with Spotter Buoys (PacWave Test Facility South) |  | #NAME? | #NAME? | 7 | 7 | 1 | 0% | bar: 2024-05-01
M | M1B.2.1 | Spotter Buoy Measurement Campaign #1 Complete |  | #NAME? | #NAME? | 7 | 7 | - | 0% | bar: 2024-05-01
M | M1B.2.2 | Preliminary spotter buoy assessment complete |  | #NAME? | #NAME? | 7 | 7 | 1 | 0% | bar: 2024-05-01
ST | 1B.2.1 | Permitting |  | #NAME? | #NAME? | 1 | 6 | 6 | 0% | bar: 2023-11-01 to 2024-04-01
|  | File NEPA documentation for campaign #1 and 2 |  | #NAME? | #NAME? |  |  | 1 | 0% | bar: 2023-11-01
|  | Obtain NEPA authorization for campaign #1 and 2 |  | #NAME? | #NAME? |  |  | 1 | 0% | bar: 2024-04-01
|  | Deploy spotter array and carry out system test |  | #NAME? | #NAME? |  |  | 1 | 0% | bar: 2024-05-01
|  | Improve on spotter sync codes |  | #NAME? | #NAME? |  |  | 1 | 0% | bar: 2024-05-01 to 2024-12-01
ST | 1B.3 | Interface development near real-time wave measurement code and RLE |  | #NAME? | #NAME? | 8 | 10 | 3 | 0% | bar: 2024-06-01 to 2024-08-01
ST | 1B.4 | Open ocean Deployment Campaign #2 with near Real-Time Spotter Buoys and estimator |  | #NAME? | #NAME? | 15 | 15 | 1 | 0% | bar: 2025-01-01
|  | Further development of spotter sync code |  | #NAME? | #NAME? |  |  | 4 | 0% | bar: 2024-12-01 to 2025-03-01
|  | Deploy spotter array and carry out system at test site, to gather data for training estimator, and to prove out real time data transmission |  | #NAME? | #NAME? |  |  | 5 | 0% | bar: 2025-01-01
M | M1B.4.1 | Near Real-Time Spotter Buoy (with estimator) Campaign #2 Complete |  | #NAME? | #NAME? | 15 | 15 | - | 0% | bar: 2025-01-01
D | D1B.4.1 | Measurement campaign #1 and 2 report with results and lessons learned |  | #NAME? | #NAME? | 16 | 16 |  | 0% | bar: 2025-01-01
T | 2 | Plan, prepare, perform wave tank testing; analyze results | Kelson | #NAME? | #NAME? | 1 | 16
ST | 2.1 | Develop wave tank test plans |  | #NAME? | #NAME? | 1 | 4 | 4 | 0% | bar: 2023-11-01 to 2024-02-01
ST | 2.2 | Provide and prepare P1 |  | #NAME? | #NAME? | 6 | 9 | 4 | 0% | bar: 2024-04-01 to 2024-07-01
ST | 2.2.1 | Fabricate and order refurbishment parts for P1 |  | #NAME? | #NAME? | 1 | 5 | 5 | 0% | bar: 2023-11-01 to 2024-03-01
ST | 2.2.2 | Develop and build v1 of power electronics package |  | #NAME? | #NAME? | 1 | 4 | 4 | 0% | bar: 2023-11-01 to 2024-02-01
ST | 2.3 | Carry out tank test cycle #1 and analyze results |  | #NAME? | #NAME? | 12 | 12 | 1 | 0% | bar: 2024-10-01
M | M2.3.1 | Hydrodynamic parameters obtained for use in refining WEC-Sim model and baseline controller performance established |  | #NAME? | #NAME? | 12 | 12 | - | 0% | bar: 2024-10-01
ST | 2.4 | Carry out tank test cycle #2 and analyze results |  | #NAME? | #NAME? | 14 | 14 | 1 | 0% | bar: 2024-12-01
M | M2.4.1 | Initial NeuralWEC system wave tank testing complete. Analyze results and compare to goal metrics in Table 1 and anticipated simulation findings |  | #NAME? | #NAME? | 14 | 14 | - | 0% | bar: 2024-12-01
ST | 2.5 | Carry out tank test cycle #3 and analyze results |  | #NAME? | #NAME? | 16 | 16 | 1 | 0% | bar: 2025-02-01
M | M2.5.1 | Wave tank testing is complete. Analyze results and compare to goal metrics in Table 1 as well as previous wave tank test. |  | #NAME? | #NAME? | 16 | 16 | - | 0% | bar: 2025-02-01
D | D2.5.1 | Wave tank testing report for all three tests with results vs goal metrics and lessons learned |  | #NAME? | #NAME? | 17 | 17 |  | 0% | bar: 2025-02-01
M | M2.5.2 | DOE review |  | #NAME? | #NAME? | 16 | 16 |  | 0% | bar: 2025-02-01
T | 3 | Develop a critical design for P2 | LPS | #NAME? | #NAME? | 1 | 19
ST | 3.1 | Define requirements |  | #NAME? | #NAME? | 1 | 2 | 2 | 0% | bar: 2023-11-01 to 2023-12-01
ST | 3.2 | Develop design for P2 in WEC-Sim |  | #NAME? | #NAME? | 3 | 5 | 3 | 0% | bar: 2024-01-01 to 2024-03-01
ST | 3.3 | Develop CAD model and shop drawings |  | #NAME? | #NAME? | 6 | 19 | 12 | 0% | bar: 2024-04-01 to 2025-04-01
D | D3.3.1 | 90% critical design for the P2 included in the continuation application and Go/No-Go presentation. |  | #NAME? | #NAME? | 19 | 19 | - | 0% | bar: 2025-04-01
T | 4 | Develop preliminary plans for fabricating, IO&M, testing & decommissioning P2 at PacWave | LPS | #NAME? | #NAME? | 1 | 22
ST | 4.1 | Preliminary contractual agreements with PacWave facility |  | #NAME? | #NAME? | 10 | 22 | 12 | 0% | bar: 2024-08-01 to 2025-08-01
ST | 4.2 | Develop preliminary test plan for PacWave |  | #NAME? | #NAME? | 2 | 19 | 22 | 0% | bar: 2023-11-01 to 2025-05-01
D | D4.2.1 | P2 Testing Plan |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2024-04-01 to 2025-05-01
ST | 4.3 | Develop fabrication plan for PacWave |  | #NAME? | #NAME? | 6 | 19 | 17 | 0% | bar: 2024-04-01 to 2025-05-01
M | M4.3.1 | 30% plan set for fabrication, mobilization, deployment and decommissioning. |  | #NAME? | #NAME? |  |  | - | 0% | bar: 2025-05-01
M | M4.3.2 | 60% plan set for fabrication, mobilization, deployment and decommissioning. |  | #NAME? | #NAME? |  |  | - | 0% | bar: 2025-05-01
D | D4.3.1 | Preliminary fabrication plan |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2025-03-01 to 2025-05-01
ST | 4.4 | Develop preliminary plans for mobilization, deployment and decommissioning, including safety training and emergency response plans |  | #NAME? | #NAME? | 6 | 19 | 17 | 0% | bar: 2024-04-01 to 2025-05-01
ST | 4.4.1 | Submit NEPA documentation/Biological Assessment for testing the P2 at PacWave South |  | #NAME? | #NAME? | 19 | 22 | 1 | 0% | bar: 2025-05-01 to 2025-08-01
D | D4.4.1 | Preliminary IO&M plan including decommissioning of P2 |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2025-05-01
T | 5 | Go/No-Go Review | LPS | #NAME? | #NAME? | 19 | 22
D | D5.0.1 | Continuation application including preliminary P2 design and budget (may include additional technical documentation identified in BP1) |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2025-05-01 to 2025-08-01
D | D5.0.2 | GNG virtual presentation |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2025-05-01 to 2025-08-01
M | M5.0.1 | Go/No-Go Decision Received |  | #NAME? | #NAME? | 19 | 19 |  | 0% | bar: 2025-05-01 to 2025-08-01
ST | 5.1 | Negotiations of BP2 (or Closeout of BP1) depending on the GNG decision |  | #NAME? | #NAME? | 20 | 22 | 1 | 0% | bar: 2025-05-01 to 2025-08-01
ST | 5.2.1 | Bridge tasks occur |  | #NAME? | #NAME? | 20 | 22 | 3 | 0% | bar: 2025-06-01 to 2025-08-01
BP | Budget Period 2 Begins
T | 6 | Update design and plan set for P2 based on DOE feedback | LPS | #NAME? | #NAME? | 23 | 48
ST | 6.1 | Detailed engineering drawings, fabrication plans, test plans, deployment/ decommissioning plans |  | #NAME? | #NAME? | 23 | 26 | 4 | 0% | bar: 2025-09-01 to 2025-12-01
D | D6.1.1 | Detailed engineering drawings |  | #NAME? | #NAME? | 26 | 26 | 0 | 0% | bar: 2025-12-01
D | D6.1.2 | Detailed test plan |  | #NAME? | #NAME? | 26 | 26 | 0 | 0% | bar: 2025-12-01
D | D6.1.3 | Detailed IO&M and decommissioning plan |  | #NAME? | #NAME? | 26 | 26 | 0 | 0% | bar: 2025-12-01
D | D6.1.4 | Detailed Fabrication Plan |  | #NAME? | #NAME? | 26 | 26 | 0 | 0% | bar: 2025-12-01
M | M6.1.1 | DOE design review completed |  | #NAME? | #NAME? | 26 | 26 | 0 | 0% | bar: 2025-12-01 to 2026-01-01
ST | 6.2 | Consultation regarding updating control for PacWave |  | #NAME? | #NAME? | 23 | 48 | 25 | 0% | bar: 2025-09-01 to 2027-10-01
ST | 6.3 | Software maturation and data analysis |  | #NAME? | #NAME? | 24 | 26 | 3 | 0% | bar: 2025-10-01 to 2025-12-01
ST | 6.4 | Purchase long lead items (e.g. generators, composite parts requiring tooling, etc., typical motor/generator quoted at 32-wk lead time, position indexer quoted at 43 wk lead time) |  | #NAME? | #NAME? | 23 | 29 | 6 | 0% | bar: 2025-09-01 to 2026-03-01
T | 7 | Fabricate P2 | LPS | #NAME? | #NAME? | 24 | 41
ST | 7.1 | Composite fabrication |  | #NAME? | #NAME? | 24 | 36 | 9 | 0% | bar: 2026-02-01 to 2026-10-01
ST | 7.2 | Metal fabrication |  | #NAME? | #NAME? | 26 | 36 | 7 | 0% | bar: 2026-03-01 to 2026-10-01
ST | 7.3 | Generator and electrical component procurement |  | #NAME? | #NAME? | 27 | 38 | 6 | 0% | bar: 2026-07-01 to 2026-12-01
ST | 7.4 | Assembly and fabrication inspection by DOE |  | #NAME? | #NAME? | 33 | 39 | 1 | 0% | bar: 2027-01-01
ST | 7.5 | Ship to Port of Newport, OR |  | #NAME? | #NAME? | 33 | 40 | 1 | 0% | bar: 2027-02-01
M | M7.5.1 | P2 delivered to test site |  | #NAME? | #NAME? | 33 | 40 | - | 0% | bar: 2027-02-01
M | M7.5.2 | DOE Review |  | #NAME? | #NAME? | 41 | 41 | bar: 2027-02-01
T | 8 | Deploy P2 per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 34 | 41
ST | 8.1 | Staging |  | #NAME? | #NAME? | 34 | 41 | 1 | 0% | bar: 2027-03-01
ST | 8.2 | Load-in and assembly |  | #NAME? | #NAME? | 34 | 41 | 1 | 0% | bar: 2027-03-01
ST | 8.3 | Final survey/reconnaissance of PacWave test berth |  | #NAME? | #NAME? | 34 | 41 | 1 | 0% | bar: 2027-03-01
ST | 8.4 | Set mooring, connect umbilical cable, and deploy WEC & Spotters |  | #NAME? | #NAME? | 34 | 41 | 1 | 0% | bar: 2027-03-01
T | 9 | Test P2 at PacWave South, per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 34 | 45
D | D9.01 | P2 / MPC / RLE Test and Operations Report |  | #NAME? | #NAME? | 45 | 45 |  | 0% | bar: 2027-04-01
D | D9.02 | Data delivered to MHKDR/Tethys/Tethys Engineering |  | #NAME? | #NAME? | 45 | 45 |  | 0% | bar: 2027-04-01
ST | 9.1 | Baseline testing |  | #NAME? | #NAME? | 35 | 42 | 1 | 0% | bar: 2027-04-01
ST | 9.2 | MPC and RLE testing with continual evaluation |  | #NAME? | #NAME? | 36 | 45 | 3 | 0% | bar: 2027-05-01 to 2027-07-01
ST | 9.3 | P2 performance analysis/ Accreditation testing |  | #NAME? | #NAME? | 37 | 45 | 2 | 0% | bar: 2027-06-01 to 2027-07-01
T | 10 | Decommission P2 per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 39 | 46
D | D10.0.1 | Decomissioning report and lessons learned |  | #NAME? | #NAME? | 46 | 46 |  | 0% | bar: 2027-08-01
ST | 10.1 | Safety reconnaissance |  | #NAME? | #NAME? | 39 | 46 | 1 | 0% | bar: 2027-08-01
ST | 10.2 | P2 and Spotter buoy retrieval |  | #NAME? | #NAME? | 39 | 46 | 1 | 0% | bar: 2027-08-01
ST | 10.3 | Cable & mooring retrieval |  | #NAME? | #NAME? | 39 | 46 | 1 | 0% | bar: 2027-08-01
ST | 10.4 | Anchor retrieval |  | #NAME? | #NAME? | 39 | 46 | 1 | 0% | bar: 2027-08-01
ST | 10.5 | Clean, disassemble, inventory and store equipment for future use |  | #NAME? | #NAME? | 39 | 46 | 1 | 0% | bar: 2027-08-01
T | 11 | Final analysis and report | LPS | #NAME? | #NAME? | 43 | 48
ST | 11.1 | Update WEC-Sim full sized device simulation |  | #NAME? | #NAME? | 43 | 47 | 5 | 0% | bar: 2027-05-01 to 2027-09-01
D | D11.1.1 | Data submitted to MHKDR/Tethys/Tethys Engineering |  | #NAME? | #NAME? | 48 | 48 |  | 0% | bar: 2027-08-01 to 2027-10-01
ST | 11.2 | Compare WEC-Sim results to Table 1 |  | #NAME? | #NAME? | 46 | 48 | 3 | 0% | bar: 2027-08-01 to 2027-10-01
ST | 11.3 | Write the Final Technical Report |  | #NAME? | #NAME? | 48 | 48 | 1 | 0% | bar: 2027-10-01
D | D11.3.1 | Final Technical Report including final project goal metrics results |  | #NAME? | #NAME? | 48 | 48
D | D11.3.2 | LCOE analysis using SAM |  | #NAME? | #NAME? | 48 | 48

## Hot Sheet Tasks
Hot sheet for tasks coming up:
T/ST/M/D | Task #'s | Task | Leader | Start date | End date | Start month | End month | %
#REF! | 1 | Simulations | #REF! | 2023-11-01 | 2024-08-30 | 1 | 36 | 0
#REF! | 0 | Initial Lit Review | #REF! | 2023-11-01 | 2023-11-30 | 1 | 1 | 100%
#REF! | 0 | 2D IASA and hologram reconstruction | #REF! | 2023-11-01 | 2023-11-30 | 1 | 1 | 0%
#REF! | 0 | COMSOL | #REF! | 2023-12-01 | 2024-01-30 | 2 | 3 | 0%
#REF! | 0 | Metamaterial design | #REF! | 2024-07-01 | 2024-08-30 | 9 | 10 | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | 2 | Prototyping | #REF! | 2023-12-01 | 2025-05-30 | 2 | 19 | 0%
#REF! | 0 | 2D Prototype | #REF! | 2023-12-01 | 2024-03-01 | 2 | 4 | 0%
#REF! | 0 | 3D Prototype | #REF! | 2024-03-01 | 2024-06-30 | 5 | 8 | 0%
#REF! | 0 | Metamaterial prototyping | #REF! | 2024-09-01 | 2025-03-02 | 11 | 16 | 0%
#REF! | 0 | Final Prototype | #REF! | 2025-01-01 | 2025-05-30 | 15 | 19 | 0%
#REF! | 0 | Metamaterial lab testing | #REF! | 2024-12-01 | 2025-03-02 | 14 | 16 | 0%
#REF! | 0 | Final prototype user testing | #REF! | 2025-03-01 | 2025-05-30 | 17 | 19 | 0%
#REF! | 5 | Business | #REF! | 2024-04-01 | 2025-03-02 | 6 | 16 | 0%
#REF! | 0 | Market targetted | #REF! | 2024-04-01 | 2024-04-30 | 6 | 6 | 0%
#REF! | 0 | Hire engineers, ops, manufacturing | #REF! | 2025-02-01 | 2025-03-02 | 16 | 16 | 0%
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | Kelson | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## Adjusted for no work in bridge (hidden)
DE-EE-0009957 GANTT CHART
| OVERALL PROJECT STATUS |  | Green.red. yellow??? set this up base on current date, percentage of task supposed to be done by current datea nd percentage actually done by current date. |  |  |  |  | CURRENT DATE | [6 empty] | 2023-12-10 | [6 empty] | LAST EDITED | [6 empty] | 2023-05-11
| PROJECT TITLE |  | EE0009957 |  |  |  |  | COMPANY NAME | [6 empty] | Littoral Power Systems
| PROJECT MANAGER |  | Sydney Platt |  |  |  |  | PROJECT START DATE | [6 empty] | 2023-05-01
| TASK NUMBER | TASK TITLE | TASK OWNER | START DATE | END DATE | START MONTH | END MONTH | DURATION | PROGRESS | BP1 (19M, 3M Bridge) | [21 empty] | BP2 (26 M)
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
 | time axis 2023-05-01 to 2027-04-01
 | time axis 2023-05-01 to 2027-04-01
| Budget Period 2 Begins |  |  | #NAME?
T | 0 | Project Management | LPS | #NAME? | #NAME? | 1 | 48 | #NAME?
ST | 0.1 | Project Management Plan |  | #NAME? | #NAME? | 1 | 1 | 1 | 10%
M | M0.1.1 | Project management plan is complete. |  | #NAME? | #NAME? | 1 | 1 | 1 | 10%
D | D0.1.1 | Project management plan (5–10-page document that augments the SOPO and RPPR2) |  | #NAME? | #NAME? | 2 | 2 | #NAME? | 0%
ST | 0.2 | Diversity, Equity and Inclusion Plan |  | #NAME? | #NAME? | 1 | 48 | #NAME? | 0%
M | M0.2.1 | Identified economically challenged coastal communities (such as Angoon AK) and reported on the alignment of this technology with the community’s needs as part of the Go/No-Go |  | #NAME? | #NAME? | 22 | 22 | #NAME? | 0%
M | M0.2.2 | Established a written employee recruitment plan |  | #NAME? | #NAME? | 6 | 6 | #NAME? | 0%
D | D0.2.1 | Employee recruitment plan |  | #NAME? | #NAME? | 7 | 7 | #NAME? | 0%
M | M0.2.3 | Implemented a key element of the recruiting plan, e.g., attended a career fair |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
M | M0.2.4 | Implemented another key element of the recruiting plan, e.g., attended another career fair |  | #NAME? | #NAME? | 36 | 36 | #NAME? | 0%
M | M0.2.5 | Subaward template modified to include the requirement that subrecipients provide a DEI plan and that they report on progress against that plan for the Go/No-Go and at the end of the project |  | #NAME? | #NAME? | 2 | 2 | #NAME? | 0%
M | M0.2.6 | Established a plan to provide outreach and education about this project |  | #NAME? | #NAME? | 15 | 15 | #NAME? | 0%
D | D0.2.2 | DEI engagement plan |  | #NAME? | #NAME? | 15 | 15 | #NAME? | 0%
M | M0.2.7 | Implemented a key element of the outreach plan, e.g., partnered with TRiO and gave a talk at New Bedford High School |  | #NAME? | #NAME? | 24 | 24 | #NAME? | 0%
D | D0.2.3 | Reoccurring Diversity, Equity, and Inclusion Activities Project Reporting as part of quartlery Research Performance Progress Report (RPPR) |  | #NAME? | #NAME? | 1 | 48 | #NAME? | 0%
ST | 0.3 | Develop preliminary commercialization plan |  | #NAME? | #NAME? | 1 | 48 | #NAME? | 0%
M | M0.3.1 | Conversations with 5 potential customers are complete and notes from each have been recorded |  | #NAME? | #NAME? | 8 | 8 | #NAME? | 0%
D | D0.3.1 | House of Quality analysis |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
M | M0.3.2 | Customer conversations have been analyzed to determine the most feasible market to pursue |  | #NAME? | #NAME? | 20 | 20 | #NAME? | 0%
M | M0.3.3 | Minimum viable product (MVP) and pricing strategy have been specified. |  | #NAME? | #NAME? | 27 | 27 | #NAME? | 0%
M | M0.3.4 | Key risks to producing the MVP have been identified |  | #NAME? | #NAME? | 40 | 40 | #NAME? | 0%
D | D0.3.2 | Preliminary Commercialization Plan |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
ST | 0.4 | Manage Risks |  | #NAME? | #NAME? | 1 | 48 | #NAME? | 0%
D | D0.4.1 | Updated project and technical risk register delivered at start of project and updated for Go/No Go aplication |  | #NAME? | #NAME? | 19 | 19 | #NAME? | 0%
ST | 0.5 | Data Management Plan |  | #NAME? | #NAME? | 1 | 48 | #NAME? | 0%
T | 1 | Develop wave estimation technique and the NeuralWEC supervisory control | GE | #NAME? | #NAME? | 2 | 22 | #NAME?
ST | 1.1 | Develop preliminary version of AI-based Fast Surrogate Model (AIFSM) of the plant |  | #NAME? | #NAME? | 2 | 7 | #NAME? | 0%
M | M 1.1.1. | WEC-Sim model, baseline controller, sensor model and API supplied to controls software experts. |  | #NAME? | #NAME? | 2 | 2 | #NAME? | 0%
ST | 1.2 | Receive, test, and benchmark preliminary WEC-Sim model |  | #NAME? | #NAME? | 2 | 2 | #NAME? | 0%
ST | 1.3 | Develop preliminary version of the scheduled full-state MPC-based controllers |  | #NAME? | #NAME? | 2 | 6 | #NAME? | 0%
M | M1.3.1 | The controller is demonstrated on WEC-Sim model |  | #NAME? | #NAME? | 6 | 6 | #NAME? | 0%
ST | 1.4 | Develop preliminary version of RLE for estimation of wave forcing based on sea states |  | #NAME? | #NAME? | 2 | 9 | #NAME? | 0%
ST | 1.5 | Collaborate on wave tank test plan and wave tank sensor selection |  | #NAME? | #NAME? | 2 | 4 | #NAME? | 0%
ST | 1.6 | Update MPC control strategy for use with developed RLE |  | #NAME? | #NAME? | 6 | 12 | #NAME? | 0%
ST | 1.7 | Deploy first versions of RLE/MPC on selected control platform |  | #NAME? | #NAME? | 7 | 12 | #NAME? | 0%
M | M1.7.1 | RLE and controller deployed on control platform |  | #NAME? | #NAME? | 12 | 12 | #NAME? | 0%
ST | 1.7.1 | Process ocean buoy wave data using RLE in emulator mode |  | #NAME? | #NAME? | 8 | 11 | #NAME? | 0%
ST | 1.8 | Control hardware integration |  | #NAME? | #NAME? | 10 | 12 | #NAME? | 0%
ST | 1.9 | Refine controller and RLE |  | #NAME? | #NAME? | 11 | 19 | #NAME? | 0%
ST | 1.1 | Finalize selection of desired measurements and collaborate on sensor selection for the P2 |  | #NAME? | #NAME? | 16 | 17 | #NAME? | 0%
ST | 1.11 | Continuing Application’s controller and RLE components |  | #NAME? | #NAME? | 18 | 19 | #NAME? | 0%
ST | 1.12 | Documentation and packaging of RLE and MPC |  | #NAME? | #NAME? | 20 | 22 | #NAME? | 0%
D | D1.12.1 | RLE & MPC development code on Github and deployed on selected control hardware for wave tank testing. |  | #NAME? | #NAME? | 22 | 22 | #NAME? | 0%
D | D1.12.2 | Data, including any tabular data, time series data, code, software, or APIs suitable for public release should be uploaded to the MHK data repository or MHKDR. |  | #NAME? | #NAME? | 22 | 22 | #NAME? | 0%
T | 1B | Wave Measurement (Wave-by-Wave Spotter Buoy Development and Field Testing) | LPS | #NAME? | #NAME? | 1 | 16 | #NAME?
ST | 1B.1 | Near Real-Time RF Spotter Buoy Customization |  | #NAME? | #NAME? | 1 | 6 | #NAME? | 0%
|  | Develop preliminary spotter sync code |  | #NAME? | #NAME? |  |  | #NAME? | 0%
ST | 1B.2 | Open ocean Deployment Campaign #1 with Spotter Buoys (PacWave Test Facility South) |  | #NAME? | #NAME? | 7 | 7 | #NAME? | 0%
M | M1B.2.1 | Spotter Buoy Measurement Campaign #1 Complete |  | #NAME? | #NAME? | 7 | 7 | #NAME? | 0%
M | M1B.2.2 | Preliminary spotter buoy assessment complete |  | #NAME? | #NAME? | 7 | 7 | #NAME? | 0%
ST | 1B.2.1 | Permitting |  | #NAME? | #NAME? | 1 | 6 | #NAME? | 0%
|  | File NEPA documentation for campaign #1 and 2 |  | #NAME? | #NAME? |  |  | #NAME? | 0%
|  | Obtain NEPA authorization for campaign #1 and 2 |  | #NAME? | #NAME? |  |  | #NAME? | 0%
|  | Deploy spotter array and carry out system test |  | #NAME? | #NAME? |  |  | #NAME? | 0%
|  | Improve on spotter sync codes |  | #NAME? | #NAME? |  |  | #NAME? | 0%
ST | 1B.3 | Interface development near real-time wave measurement code and RLE |  | #NAME? | #NAME? | 8 | 10 | #NAME? | 0%
ST | 1B.4 | Open ocean Deployment Campaign #2 with near Real-Time Spotter Buoys and estimator |  | #NAME? | #NAME? | 15 | 15 | #NAME? | 0%
|  | Further development of spotter sync code |  | #NAME? | #NAME? |  |  | #NAME? | 0%
|  | Deploy spotter array and carry out system at test site, to gather data for training estimator, and to prove out real time data transmission |  | #NAME? | #NAME? |  |  | #NAME? | 0%
M | M1B.4.1 | Near Real-Time Spotter Buoy (with estimator) Campaign #2 Complete |  | #NAME? | #NAME? | 15 | 15 | #NAME? | 0%
D | D1B.4.1 | Measurement campaign #1 and 2 report with results and lessons learned |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
T | 2 | Plan, prepare, perform wave tank testing; analyze results | Kelson | #NAME? | #NAME? | 1 | 17 | #NAME?
ST | 2.1 | Develop wave tank test plans |  | #NAME? | #NAME? | 1 | 4 | #NAME? | 0%
ST | 2.2 | Provide and prepare P1 |  | #NAME? | #NAME? | 6 | 9 | #NAME? | 0%
ST | 2.2.1 | Fabricate and order refurbishment parts for P1 |  | #NAME? | #NAME? | 1 | 5 | #NAME? | 0%
ST | 2.2.2 | Develop and build v1 of power electronics package |  | #NAME? | #NAME? | 1 | 4 | #NAME? | 0%
ST | 2.3 | Carry out tank test cycle #1 and analyze results |  | #NAME? | #NAME? | 12 | 12 | #NAME? | 0%
M | M2.3.1 | Hydrodynamic parameters obtained for use in refining WEC-Sim model and baseline controller performance established |  | #NAME? | #NAME? | 12 | 12 | #NAME? | 0%
ST | 2.4 | Carry out tank test cycle #2 and analyze results |  | #NAME? | #NAME? | 14 | 14 | #NAME? | 0%
M | M2.4.1 | Initial NeuralWEC system wave tank testing complete. Analyze results and compare to goal metrics in Table 1 and anticipated simulation findings |  | #NAME? | #NAME? | 14 | 14 | #NAME? | 0%
ST | 2.5 | Carry out tank test cycle #3 and analyze results |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
M | M2.5.1 | Wave tank testing is complete. Analyze results and compare to goal metrics in Table 1 as well as previous wave tank test. |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
D | D2.5.1 | Wave tank testing report for all three tests with results vs goal metrics and lessons learned |  | #NAME? | #NAME? | 17 | 17 | #NAME? | 0%
M | M2.5.2 | DOE review |  | #NAME? | #NAME? | 16 | 16 | #NAME? | 0%
T | 3 | Develop a critical design for P2 | LPS | #NAME? | #NAME? | 1 | 19 | #NAME?
ST | 3.1 | Define requirements |  | #NAME? | #NAME? | 1 | 2 | #NAME? | 0%
ST | 3.2 | Develop design for P2 in WEC-Sim |  | #NAME? | #NAME? | 3 | 5 | #NAME? | 0%
ST | 3.3 | Develop CAD model and shop drawings |  | #NAME? | #NAME? | 6 | 19 | #NAME? | 0%
D | D3.3.1 | 90% critical design for the P2 included in the continuation application and Go/No-Go presentation. |  | #NAME? | #NAME? | 19 | 19 | #NAME? | 0%
T | 4 | Develop preliminary plans for fabricating, IO&M, testing & decommissioning P2 at PacWave | LPS | #NAME? | #NAME? | 2 | 22 | #NAME?
ST | 4.1 | Preliminary contractual agreements with PacWave facility |  | #NAME? | #NAME? | 10 | 22 | #NAME? | 0%
ST | 4.2 | Develop preliminary test plan for PacWave |  | #NAME? | #NAME? | 2 | 19 | #NAME? | 0%
D | D4.2.1 | P2 Testing Plan |  | #NAME? | #NAME? | 19 | 19 | #NAME? | 0%
ST | 4.3 | Develop fabrication plan for PacWave |  | #NAME? | #NAME? | 6 | 19 | #NAME? | 0%
D | D4.3.1 | Preliminary fabrication plan |  | #NAME? | #NAME? | 19 | 19 | #NAME? | 0%
ST | 4.4 | Develop preliminary plans for mobilization, deployment and decommissioning, including safety training and emergency response plans |  | #NAME? | #NAME? | 6 | 19 | #NAME? | 0%
ST | 4.4.1 | Submit NEPA documentation/Biological Assessment for testing the P2 at PacWave South |  | #NAME? | #NAME? | 19 | 22 | #NAME? | 0%
D | D4.4.1 | Preliminary IO&M plan including decommissioning of P2 |  | #NAME? | #NAME? | 19 | 19 | #NAME? | 0%
T | 5 | Go/No-Go Review | LPS | #NAME? | #NAME? | 23 | 25 | #NAME?
D | D5.0.1 | Continuation application including preliminary P2 design and budget (may include additional technical documentation identified in BP1) |  | #NAME? | #NAME? | 23 | 23 | #NAME? | 0%
D | D5.0.2 | GNG virtual presentation |  | #NAME? | #NAME? | 23 | 23 | #NAME? | 0%
M | M5.0.1 | Go/No-Go Decision Received |  | #NAME? | #NAME? | 23 | 23 | #NAME? | 0%
ST | 5.1 | Negotiations of BP2 (or Closeout of BP1) depending on the GNG decision |  | #NAME? | #NAME? | 23 | 25 | #NAME? | 0%
ST | 5.2.1 | Bridge tasks occur |  | #NAME? | #NAME? | 23 | 25 | #NAME? | 0%
BP | Budget Period 2 Begins
T | 6 | Update design and plan set for P2 based on DOE feedback | LPS | #NAME? | #NAME? | 26 | 48 | #NAME?
ST | 6.1 | Detailed engineering drawings, fabrication plans, test plans, deployment/ decommissioning plans |  | #NAME? | #NAME? | 26 | 29 | #NAME? | 0%
D | D6.1.1 | Detailed engineering drawings |  | #NAME? | #NAME? | 29 | 29 | #NAME? | 0%
D | D6.1.2 | Detailed test plan |  | #NAME? | #NAME? | 29 | 29 | #NAME? | 0%
D | D6.1.3 | Detailed IO&M and decommissioning plan |  | #NAME? | #NAME? | 29 | 29 | #NAME? | 0%
D | D6.1.4 | Detailed Fabrication Plan |  | #NAME? | #NAME? | 29 | 29 | #NAME? | 0%
M | M6.1.1 | DOE design review completed |  | #NAME? | #NAME? | 29 | 29 | #NAME? | 0%
ST | 6.2 | Consultation regarding updating control for PacWave |  | #NAME? | #NAME? | 26 | 48 | #NAME? | 0%
ST | 6.3 | Software maturation and data analysis |  | #NAME? | #NAME? | 27 | 29 | #NAME? | 0%
ST | 6.4 | Purchase long lead items (e.g. generators, composite parts requiring tooling, etc., typical motor/generator quoted at 32-wk lead time, position indexer quoted at 43 wk lead time) |  | #NAME? | #NAME? | 26 | 32 | #NAME? | 0%
T | 7 | Fabricate P2 | LPS | #NAME? | #NAME? | 27 | 43 | #NAME?
ST | 7.1 | Composite fabrication |  | #NAME? | #NAME? | 27 | 39 | #NAME? | 0%
ST | 7.2 | Metal fabrication |  | #NAME? | #NAME? | 29 | 39 | #NAME? | 0%
ST | 7.3 | Generator and electrical component procurement |  | #NAME? | #NAME? | 30 | 41 | #NAME? | 0%
ST | 7.4 | Assembly and fabrication inspection by DOE |  | #NAME? | #NAME? | 36 | 42 | #NAME? | 0%
ST | 7.5 | Ship to Port of Newport, OR |  | #NAME? | #NAME? | 36 | 43 | #NAME? | 0%
M | M7.5.1 | P2 delivered to test site |  | #NAME? | #NAME? | 36 | 43 | #NAME? | 0%
M | M7.5.2 | DOE Review |  | #NAME? | #NAME? | 43 | 43 | #NAME? | 0%
T | 8 | Deploy P2 per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 37 | 44 | #NAME?
ST | 8.1 | Staging |  | #NAME? | #NAME? | 37 | 44 | #NAME? | 0%
ST | 8.2 | Load-in and assembly |  | #NAME? | #NAME? | 37 | 44 | #NAME? | 0%
ST | 8.3 | Final survey/reconnaissance of PacWave test berth |  | #NAME? | #NAME? | 37 | 44 | #NAME? | 0%
ST | 8.4 | Set mooring, connect umbilical cable, and deploy WEC & Spotters |  | #NAME? | #NAME? | 37 | 44 | #NAME? | 0%
T | 9 | Test P2 at PacWave South, per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 44 | 48 | #NAME?
D | D9.01 | P2 / MPC / RLE Test and Operations Report |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
D | D9.02 | Data delivered to MHKDR/Tethys/Tethys Engineering |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
ST | 9.1 | Baseline testing |  | #NAME? | #NAME? | 44 | 45 | #NAME? | 0%
ST | 9.2 | MPC and RLE testing with continual evaluation |  | #NAME? | #NAME? | 45 | 46 | #NAME? | 0%
ST | 9.3 | P2 performance analysis/ Accreditation testing |  | #NAME? | #NAME? | 46 | 47 | #NAME? | 0%
T | 10 | Decommission P2 per plan developed in Subtask 4.4 and finalized in Task 6 | LPS | #NAME? | #NAME? | 47 | 48 | #NAME?
D | D10.0.1 | Decomissioning report and lessons learned |  | 2027-03-01 | #NAME? | 47 | 47 | #VALUE! | 0%
ST | 10.1 | Safety reconnaissance |  | 2027-03-01 | 2027-03-01 | 47 | 47 | #VALUE! | 0%
ST | 10.2 | P2 and Spotter buoy retrieval |  | 2027-03-01 | 2027-03-01 | 47 | 47 | #VALUE! | 0%
ST | 10.3 | Cable & mooring retrieval |  | 2027-03-01 | 2027-03-01 | 47 | 47 | #VALUE! | 0%
ST | 10.4 | Anchor retrieval |  | 2027-03-01 | 2027-03-01 | 47 | 47 | #VALUE! | 0%
ST | 10.5 | Clean, disassemble, inventory and store equipment for future use |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
T | 11 | Final analysis and report | LPS | #NAME? | #NAME? | 43 | 48 | #NAME?
ST | 11.1 | Update WEC-Sim full sized device simulation |  | #NAME? | #NAME? | 43 | 47 | #NAME? | 0%
D | D11.1.1 | Data submitted to MHKDR/Tethys/Tethys Engineering |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
ST | 11.2 | Compare WEC-Sim results to Table 1 |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
ST | 11.3 | Write the Final Technical Report |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
D | D11.3.1 | Final Technical Report including final project goal metrics results |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
D | D11.3.2 | LCOE analysis using SAM |  | #NAME? | #NAME? | 48 | 48 | #NAME? | 0%
Formulas:
COMPANY NAME = DATEDIF(DATEVALUE([START DATE]),DATEVALUE([END DATE]),"M")+1
Note on B108: @kleighton@littoralpower.com When you have time this week can I go over the changes to the schedule that I made. The way I compressed it I believe makes sense and I will send into Elaine once we have chatted it through. _Assigned to Kathie Leighton_ -Sydney Platt _Marked as done_ -Kathie Leighton _Re-opened_ Hi Sydney, I looked it over and it looks good. It looks to me like everything for Budget Period 1 necessary for a comprehensive continuation application is done before the GNG. The entire project is done in 48 months. So it is good to go. Kindly, Kathie Katherine (Kathie) Leighton ¦ Vice President she/her [image: 5312_logo_finalVERYSMALL-jpeg] Littoral Power Systems, Inc. 5 Dover Street, Suite 102 New Bedford, MA 02740 www.littoralpower.com Updated! Take a look. 508.436.4107 direct 610.207.5835 mobile -Kathie Leighton

## Labor Hours Tracker (hidden)
|  |  |  | 2022 | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026
TASK | OWNER | PEOPLE | HOURS ESTIMATED | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | TOTAL ACTUAL HOURS
0 | LPS | David Duquette | 114
|  | Sydney Platt | 371
Kathie Leighton
|  | Ryan Cook | 104
|  | Ravi Challa Ph.D. | 104
Lisa Amaral
1 | LPS | David Duquette
Sydney Platt
Ryan Cook
Ravi Challa Ph.D.
| GE | Subhrajit Roychowdhury Ph.D.
Brain Templeton Ph.D.
GE project Engineer
1B | LPS | David Duquette
Sydney Platt
Ravi Challa Ph.D.
Ryan Cook
Lisa Amaral
Brain Templeton Ph.D.
Subhrajit Roychowdhury Ph.D.
2 | Kelson
3 | LPS
4 | LPS
5 | LPS
6 | LPS
7 | LPS
8 | LPS
9 | LPS
10 | LPS
11 | LPS